## DASHBOARD
TOP TEN Item | Investigation of Issue | Training/Communication | System Functionality Discovery | Requirements Gathering / Specification Writing | Development | Testing | Ready/In Production
| Outside of LDMO |  | LDMO Tasks |  |  |  |  | Notes
Academic Standing Processing | [7 empty] | Ongoing analysis and discussions in functional office(s) to identify specific tasks; nothing for LDMO at this time.
Degree Audits | [7 empty] | Ongoing analysis and discussions in functional office(s) to identify specific tasks; nothing for LDMO at this time.
Duplicates & Merges | [5 empty] | 1 | 1 | Process to identify duplicates in Production, working out details on all merge scenarios.
Graduation Processing | [7 empty] | Ongoing analysis and discussions in functional office(s) to identify specific tasks; nothing for LDMO at this time.
Leaving the University | [7 empty] | Ongoing analysis and discussions in functional office(s) to identify specific tasks; nothing for LDMO at this time.
National Student Clearinghouse | [7 empty] | Ongoing analysis and discussions in functional office(s) to identify specific tasks; nothing for LDMO at this time.
Notifications of Changes |  |  |  | 1 |  | 2 |  | Three items identified so far.
Prequisite Checking |  |  | 1 |  |  |  |  | Registration is prevented for courses with prereqs set up; process to identify students who don't meet prereqs in Discovery.
Transfer Credit |  |  | 12 | 1 | 2 | 1 | 1 | Working group detailed 17 specific tasks; methodically moving forward.
User Experience |  |  |  | 2 | 4 | 2 | 1 | Nine specific requests identified.

## Detail
TOP TEN Item | Actionable Solution Steps | Description | Main Contact
Academic Standing Processing | ARISSA & Undergraduate Ed involved in looking at policy & processes. Faculty Senate is still considering changes to the policy. Until a final policy is in place, OUR will continue with the current process. | Concerns include preparation, corrections, and validation of student records | David Smith - drs46 Bob Kubat - rak28
Degree Audits | Group will develop best practices, tips and tricks, and what to avoid documents. Initial analysis complete, and OUR submitted four enhancement requests 2/8/18. | Audits are extremely complicated and there is a lot of programming behind the scenes; issues cited include too many clicks/pages required to find data, to make substitutions, or do any other editing | Karen Henninger - klb4
Duplicates & Merges | DT0355: Identification of duplicates - in PRD 1/19/18. Process will run for several days to identify duplicates, merging/cleaning up will still require manual interention. Functional offices are testing. 1/31/18 found an issue, looking at it technically. Will run the "identify duplicates" process by 2/12/18. | The existence of multiple IDs for a single person is an ongoing issues that raises concerns for reporting, compliance, and customer service. Resolving these is now an entirely manual process shared across numerous functional offices | Keith Brautigam - kab65
Graduation Processing | Initial analysis complete, and OUR submitted seven enhancement requests 2/8/18. | Tracking, Checkout, Review, Degree Conferral; Partially related to the “new” process of approving students to graduate | David Smith - drs46 Barbara Barr - bab13
Leaving the University |  | Withdrawal - When an Active student decides to leave the University Withdrawal - When an Active student with enrollment and disbursed aid decides to leave the University | Tryphena Miska - tma140
National Student Clearinghouse |  | Monthly processing that takes 8-16 hours to run/compile; Accurate reporting is important in determining whether a student should be placed into a repayment status for their federal student loans or whether they are eligible for interest subsidy based on their degree program | Cindy Heaton - cch16 Kaitlyn Roberts - ksr178
Notifications of Changes | Created communications matrix to ask students questions, crossover with User Experience | Concerns about students or staff being overwhelmed with emails/notices | Tim Radio - tjr190
Notifications of Changes | DT1193: Update Change of Campus per TASK0070349 in Testing. | Concerns about students or staff being overwhelmed with emails/notices | Tim Radio - tjr190
Notifications of Changes | Wait List communications - working out tech/student UI requirements, how students can opt-out, and migration of changes. Close to bringing OUR into discussion of actual text. Targeting release for mid-March 2018 (in place for Fall). | Concerns about students or staff being overwhelmed with emails/notices | Tim Radio - tjr190
Prequisite Checking | DT1237/SR095: Oracle service request SR3-16143228231 in PRD 12/14/17. | Enforced Prerequisites were rolled out to a couple of Colleges as a pilot and PERC (Post Enrollment Requirement Checking) process can be run any time | Paula Hamaty - pkr101
Prequisite Checking | IST/DS implemented for Summer 2018, waiting for SRA to go through Curricular Affairs. Science query moved to PRD. | Enforced Prerequisites were rolled out to a couple of Colleges as a pilot and PERC (Post Enrollment Requirement Checking) process can be run any time | Paula Hamaty - pkr101
Transfer Credit | DT0916: transfer credit Unpost - in Testing. | Manual course, test, and other credit models cannot be mass updated via batch process. Manual transfer models must be updated individually to add additional credit or update academic program and articulation term. | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit | DT1114: Transfer Credit Tool - in Development. | The Penn State XFR Search navigation in LionPATH is not intuitive or user-friendly. This inhibits faculty and staff from best serving students looking for transfer course evaluations. The tool is not available to current or prospective Penn State students. | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit | DT1115: CSRS mapping changes - in Technical Rework. | CSRS (Course Substitution & Request System) receives incomplete LionPATH transfer course, test, and other credit data needed to function efficiently. | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit | DT1208: transfer credit "dropping" - in PRD 11/14/17. | Transfer credit exceptions entered by college records staff sometimes drop from the audit and may need to be re-entered by staff when a student resubmits an updated transcript from a transferring institution. | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit | DT1235/SR051: Batch process - with functional team for spec requirements/spec writing. | Adding transfer credits for continuing Penn State students in LionPATH: Credit must be added and manually posted while automated batch processes continue to cause problems. This is a time consuming manual process that should be automated. (INC0689739) | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit |  | Adding transfer credits for admitted and continuing Penn State students: External catalog for each organization must be built. This process includes building the external catalog for each organization, adding credit to a student's record--either manually or pulling from the articulation tables--, flagging pertinent courses as non-transferable on the overall tables, and finalizing the offer. This is a time consuming manual process that should be automated. | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit |  | All current student credit is being added on Course Credits-Manual, and a $25 per transcript processing fee is being assigned. Once batch processes for current students are working, Undergraduate Admissions will need to bill for transcript processing on Course Credits-Automated. (INC0692430) | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit |  | Enhancement needed for the existing TRN XFRPEN (transfer course pending review) to TRN XFRGEN (transfer course general credit) “flip” process. (DT0469) | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit |  | In accordance with Faculty Senate policy, transfer course articulation rules will expire every 5 years and require academic discipline faculty to review the new courses. Business process decisions need to be made on how to handle this process before a development solution can be crafted to meet these needs. | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit |  | In LionPATH, there is not a university-wide location for faculty and staff to view/add external organization comments. The historical comments from ISIS have not been migrated into LionPATH. | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit |  | The assignment of fractional credits for transfer courses in Admissions require additional manipulation on the audit when substitution is required. | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit |  | The process for managing post-MATR changes, which impact transfer credit models is manual and multi-step and requires action needed by both Undergraduate Admissions and the University Registrar. | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit |  | There are existing limitations with the display on the Transfer Credit: Report and Academic Requirements pages. These issues cause confusion for students and advisers. (DT1113) | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit |  | Transfer articulation rules for external institutions with multiple term types (i.e. semester term type until spring 2001, then switched to quarter tem type) are not accurate. Due to effective dating and articulation rule set up, LionPATH does not handle the course articulation rules well for these type of external institutions. (DT0994) | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit |  | Transfer evaluation workflow and processing offers of admission (including adding credits): When a transfer student is deemed admissible, an offer only comes after transfer credit has been added. The process of reviewing transfer applications relies heavily on manually reviewing queries from LionPATH and viewing documents in Docfinity and in paper form. Admissions offers are delayed due to the time needed to process transfer credit in LionPATH. | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit |  | Undergraduate Admissions is not able to add in progress transfer course work, because it can have a negative impact on the degree audit. The degree audit fulfills a degree requirement with an in progress transfer course, and the student may not actually complete that course at their previous institution. Conversely, by not adding in progress transfer courses, when a student submits their final external institution transcript, they may have already taken a Penn State course that meets the same degree audit requirement. | Amanda Maxson - ahl10 Michele Rice - smr57
Transfer Credit |  | When creating a brand new set of articulation rules, process AD038 creates the Program Source Equivalency, but only for the Academic Program for which the initial student was admitted. The process needs to repeat the creation for the additional 23 UGRD Academic Programs. (DT0868) | Amanda Maxson - ahl10 Michele Rice - smr57
User Experience | Created communications matrix to ask students questions, looking into/crossing over with notification framework |  | Deb Simpson - dys11
User Experience | DT0982: Batch assignment of advisers - in Development/rework. | Issues cited include: insufficient search parameters, too many clicks/pages required to find data, default values on pages, or data in other systems that doesn’t match LP | Deb Simpson - dys11
User Experience | DT1171: iCal for student schedule - in Development. | -iCal (downloadable schedule) | Deb Simpson - dys12
User Experience | DT1180: CPPS Stack - in technical rework. DT1162, 1163, 1164, 1180, 1204: Search & Display Fields - functional specs being written. | Issues cited include: insufficient search parameters, too many clicks/pages required to find data, default values on pages, or data in other systems that doesn’t match LP | Deb Simpson - dys11
User Experience | DT1219: public.lionpath.psu.edu & Delegation - in Testing. Getting feedback from Governance/ leadership, making some adjustments, new public site launch delayed a couple of days, expected mid-February. | -public.lionpath.psu.edu | Deb Simpson - dys11
User Experience | DT1222: My Final Exam pagelet - in PRD 12/7/17. |  | Deb Simpson - dys11
User Experience | DT1249, 1250, 1251: UI Accessibility updates - functional specs written, in Development queue. | -Accessibility gains | Deb Simpson - dys11
User Experience | DT1266 : TASK0087492 - Financial Aid Intake Work Center - assigned to LDMO Business Analyst, expected go-live mid-February 2018. | Work Centers | Deb Simpson - dys11
User Experience | DT1270: TASK0088784 - Schedule of Courses Work Center - assigned to LDMO Business Analyst. | Work Centers | Deb Simpson - dys11
User Experience | DT1294: TASK0090392 - Re-enrollment Work Center - assigned to LDMO Business Analyst. | Work Centers | Deb Simpson - dys11