## DASHBOARD
TOP TEN Category | Investigation of Issue(s) | Training/ Communication | Discovery | Requirements Gathering / Specification Writing | Development | Testing | Ready/In Production
| Outside of LDMO |  | LDMO Tasks |  |  |  |  | Notes
Academic Standing Processing | [6 empty] | 1 | Functional office analysis. New policy passed by Faculty Senate April 2018. Reports provided to OUR are working; nothing for LDMO at this time. | 1
Degree Audits |  |  | 4 | 1 |  |  | 1 | Reviewing functionality and identifying barriers and potential solutions. Update to What-If in Production. | 6
Duplicates & Merges | [5 empty] | 1 | 2 | Process to identify duplicates in Production, working out details on all merge scenarios. | 3
Graduation Processing |  |  | 1 | 1 |  |  | 2 | Graduation Tracker (June) and Work Center (August) in Production. | 4
Leaving the University |  |  | 1 |  |  |  | 1 | Messaging updated (April); OUR, OSA, and Bursar agreed on request awaiting prioritization. | 2
National Student Clearinghouse | [6 empty] | 1 | LDMO and OUR analysis of reporting continues; no specific tasks for LDMO at this time. | 1
Notifications of Changes |  |  |  | 2 |  |  | 3 | Notification Working Group outlining rules/procedures for notifications. Students now notified about grades and wait lists. | 5
Prequisite Checking |  |  |  | 1 |  |  | 2 | Process can be run, including communications. OUR has done training. OUR will continue to bring departments/units/Colleges on board. | 3
Transfer Credit |  |  | 10 | 3 | 2 | 0 | 4 | Transfer Credit Tool and fixes to daily batch procedures in Production. Methodically moving forward. | 19
User Experience |  |  | 3 | 1 | 3 |  | 10 | Adding more WorkCenters; identified two items from Faculty Focus Group sessions; canceled two items due to negative interactions with other mods. | 17
Totals 09/13/18 |  |  | 19 | 9 | 5 | 1 | 27 | 61
Totals 08/01/18 |  |  | 20 | 11 | 5 | 3 | 23 | 62
Totals 06/19/18 |  |  | 19 | 12 | 6 | 2 | 20 | 59
Totals 05/15/18 |  |  | 17 | 7 | 5 | 4 | 16 | 49
Totals 04/24/18 | 3 | 0 | 18 | 7 | 6 | 5 | 12 | 48
Totals 02/09/18 | 5 | 0 | 13 | 4 | 6 | 6 | 3 | 32
Original Requests | 2 | 4 | 6 | 5 | 5 | 1 | 14 | There were 31 items that could be categorized as TOP TEN from the original list (after consolidation and removal of items the funtional owners dismissed). - 45% are completed/in PRD - 35% are actively being worked (development, testing) | 31